## NCTrust Progress Dashboard
INSTITUTION	NCTrust MOU Signed	Attend Shibboleth Training	Complete InCommon Membership	Reimbursed by MCNC for 2009's InCommon Fees (only initial pilot members are eligible, reimbursement requests must be submitted by June 1, 2009)	Set Up IdP	Set Up SP	Successful Demo Participation
MCNC	10/29/08	10/21/08	11/21/08	N/A	02/27/09	Drupal (Fall 09)	Done
Wake Technical Community College	10/20/08	10/21/08	05/22/09	June 2009	07/23/09	N/A	Done
North Carolina State University	11/24/08	10/21/08	01/14/09	March 2009	08/01/08	VCL (Spring 09)	Done
UNC Chapel Hill	11/24/08	10/21/08	02/20/09	April 2009	08/01/08	N/A	Done
NC Department of Public Instruction	01/26/09	10/21/08	06/01/09	May 2009	07/24/09	CIMS (Spring 10)	Done
Rockingham County Schools	03/20/09	02/24/09	04/21/09	April 2009	05/06/09	N/A	Done
Davie County Schools	05/18/09	02/24/09	06/11/09	June 2009	06/24/09	N/A	Done
Duke University	08/22/09	10/21/08	Done	N/A	Done	N/A
Central Piedmont Community College	06/17/09	02/24/09	Done	June 2009	06/03/10	N/A
NCLive	10/20/08	10/21/08	09/11/09	N/A	N/A	NCLive (Oct 09)	Done
Charlotte-Mecklenburg Schools		02/24/09				N/A
UNC Greensboro		10/21/08	10/20/09			N/A
NC Community College System (LOR)		02/24/09				N/A

USEFUL LINKS								\
Federate ID Management Task Force:	https://edspace.mcnc.org/confluence/display/FIM/
NCTrust MOU:	https://edspace.mcnc.org/confluence/download/attachments/2818248/NCTrust-MOU.doc
NCTrust MOU Appendix:	https://edspace.mcnc.org/confluence/download/attachments/2818248/NCTrust-MOU-Appendix.doc
NCTrust MOU With Latest Signatures:	https://edspace.mcnc.org/confluence/download/attachments/7014626/NCTrust-MOU.With.Signatures.pdf
NCSU-specific MOU:	https://edspace.mcnc.org/confluence/download/attachments/7014626/NCTrust-MOU.Signed.By.NCSU.And.MCNC.pdf
NC DPI-specific MOU:	https://edspace.mcnc.org/confluence/download/attachments/7014626/NCTrust-MOU-DPI-signed.by.DPI.And.MCNC.pdf
NC DPI-specific Appendix:	https://edspace.mcnc.org/confluence/download/attachments/7014626/NCTrust-MOU-Appendix-v3-DPI.pdf
InCommon Membership Info:	http://www.incommonfederation.org/join.cfm
10/08 Shib Training Materials:	http://www.duke.edu/~shilen/shibtraining/
Shibboleth:	http://shibboleth.internet2.edu/software.html
NCTrust Shibboleth Technical References:	https://edspace.mcnc.org/confluence/display/FIM/Shibboleth+Technical+References
NCTrust IdP Appliance README:	https://edspace.mcnc.org/confluence/download/attachments/8258684/incommon-nctrust-idp-appliance.readme.txt